## Slide 1: YoungPeople@Work Mid year assessment
17 July 2015
Venue: Tygerberg Park, Parow
Facilitated by: Frank Julie

## Slide 2: Online training
Clothilda – low interest at Lavis
Link training to job/training search needs – Doreen
Issuing of cards – at Adriaanse quickly and it helps
Winter weather causing low interest
6 days more effective than 8 days
Taking the break for marketing, admin not always implemented
Nasieba to be mentored – Kensington
Nasieba to be transferred to Lavis
Sisanda – to be based at Adriaanse
Lemosa – will managed Delft
Mandi go to Bellvile – Lwandle to close down temporarily

## Slide 3: Continue
Organise youth days at libraries to promote online training
Involve library staff in youth days
Numbers at libraries
Lavis – 30
Adriaanse – 18
Lwandle – 30
Kensington - 30
Bonteheuwel – 3
Total +/- 111

## Slide 4: Computer academy
Strengths
Lizelle involvement a big change! No software/hardware problems; students are motivated when they hear about job shadowing/placements; payments huge improvement; 95% rate currently; laptops create more professional image; need a projector for PowerPoint; murals made a big impact; word of mouth is strong; strong link between online/life skills referral; Linda powerful marketing; learnerships to more formalised/follow process/check fine print; 8 students in class helps; computer manuals helped in first semester; enquiries for usb sticks especially Bellville; 17+25 = 42 registrations are more – but people drop out. 17-14-9 = 40 (Lavis) 16 registrations in Bellvillle

## Slide 5: Continue
Weaknesses
Internet access; WIFI, more chairs; access to antivirus – SDJ
Wiring in Bellville – need someone to help with wiring – SDJ
Absenteeism – winter playing a role – Lizelle
When assessments – students stay away? – CP
Non-refundable deposits – better communication is needed – Shirley
Struggles to pay fees can become a block to learning – Doreen
The period waiting for classes to start – people can change their minds; regular notifications; 6 students as cut off then Doreen and Mandi will assist with extra tuition
People with shifts – we cannot assist in future

## Slide 6: Life skills
Strengths
More people attending despite winter; marketing good; positive feedback; changing lives and mind-sets; donations good; certificate fee working to cover costs; book venue in advance due to other training; 7-8-9 Sept (phase 1) – 12-13-14-15 Oct (phase 2) more older persons attending; redesign bookkeeping; Shirley to do admin; business and entrepreneurial skills; coaching/mentoring skills to be added; must shift venue (2 Lavis and 2 Bellville); use of outside speakers is powerful (e.g. Linda/Shirley/Vicky/Doreen/Mandi/Bergman/Dineo/Sideeqa/Yolanda) ; space of sharing is powerful – sharing resources; referrals to learnerships/further training; SETA partnerships to be built for learnerships;
Weaknesses
Better feedback form needed; Volunteers allocated for tasks.

## Slide 7: Job placement and tracking
Strengths
There is a guarantee we will place; better system in place; job shadowing increasing (Prestige (2), SPP (4), Sanlam (11), YP@W (4), more learnerships/internships, Vision Homes, Radio 786, Homemark, libraries), Follow up on Dreamworker, Harambee, Rlabs referrals (need nr’s assessed/placed/accepted); formalised (although check fine print) Placement forms captured; Doreen to spend more time at libraries to download info about jobs; youngpeople.placements@gmail.com for only placement requests
Weaknesses
Cultivate more partners needed (local schools), MOU to be drawn up for continuous placements, response time, redesign form for readability;
Access to info (lack of Wifi needs to be addressed) Job shadowing in YP@W can improve; Put faces of placements in the training centre; centralised capturing of forms; task allocation to be clear;

## Slide 8: Marketing and networking
Strengths
More articles in TB; project activities like online, computer classes, youth weeks; redesigned pamphlets; radio more frequent; Facebook working well and more likes (4057 to date); check out booster facility on FB; word of mouth; name lables; murals very powerful – big response; whatsapp groups – saving us money/good response; newsletter; give hardcopy to computer students; work on hardcopy newsletter to capture success stories; Facebook stories effective; write teasers to the press and follow up with invites; identify specific national days.
Weaknesses
CTV can be improved; need more T-shirts; logo finalised; shirts to be designed; logic sms not very effective now – too costly; emailing of newsletter to students; harvest time to be continued;

## Slide 9: Networking
Strengths
Harambee, Rlabs, Career Planet (post info on website) Dreamworker (fading), DOL, UWC, TASP, JOC (Bellville), CSD, Homemark, Surplus People’s Project, Whizz ICT, Learners Movement of SA (Lemosa based in Delft), Radio 786, Radio Zibonele, Achfa Projects - Kensington, community libraries, I College
Complement what we can’t do. Add value to our work. Placement opportunities are provided.
Weaknesses
NYDA needs to be cultivated; can be come placement partners and job shadowing; don’t market us effectively; Contact them in advance to confirm placements; Northlink to be recruited;

## Slide 10: Funding and finance
Strengths – new donor on board; own income increased; good track record; better story to tell; attractive to donors; local and individual giving increased; youth is a priority focus (govt); rummage sale increased; 3rd semester R22 414 pd to date; 2nd semester +/-R25 000; 1st semester – +/- R18 000; we are still on target with our income projections @ R120 000.
KBF = 100 000 SPZA = 30 000 (30 000 outstanding) HCI = 20 000
USB = 840 / computer manuals = 515
CIP to be paid a donation in future @ R 150 pp
Increase membership fee to 15.00 from June 2015
Employed students/members to pay R50 p.m. donation

## Slide 11: Continue
Weaknesses – SARS PBO application for legal compliance; needs time
Finance
Reports – auditing good; good accountability; reduction in bank fees due to ATM use; payments on time
Increase of R250 per stipend (x 12 = 27 000)
Weaknesses:
Draft policy to be finalised; low stipends; travelling fees; create a central transport fund;

## Slide 12: Admin systems
Strengths
Good life skills support and communication; adequate resources; client reception area needed apart from CSD; needs admin assistant to job shadow permanently; Dineo to be approached
Weaknesses
Bigger printer needed; load shedding lamps needed. Stock control needs more focus; regular reminders necessary to buy stock, etc.